## Gas Leakage Testcases
|  |  |  | Date | 2022-11-16
|  |  |  | Team ID | PNT2022TMID39391
|  |  |  | Project Name | Project -Gas Leakage Detection and Monitoring system
|  |  |  | Maximum Marks | 4 marks
Test case ID | Feature Type | Component | Test Scenario | Pre-Requisite | Steps To Execute | Test Data | Expected Result | Actual Result | Status | Comments | TC for Automation(Y/N) | BUG ID | Executed By
TC_OO1 | Functional | IBM cloud | Create the IBM Cloud services which are being used in this project. | IBM Cloud Login ID & Password | 1.Go to IBM Cloud signup page 2.Enter e-mail id and other credentials 3.Enter a password | https://cloud.ibm.com/login | User should sign up IBM cloud and details should be verified | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_OO2 | Functional | IBM Cloud | Configure the IBM Cloud services which are being used in completing this project. | IBM Cloud Login ID & Password | 1.Go to Cloud login 2.Enter user ID & Password 3.Verify login by the popup display | https://cloud.ibm.com/login | User login to IBM Cloud and should be navigated to IBM Cloud dashboard page | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_OO3 | Functional | IBM Watson IoT Platform | IBM Watson IoT platform acts as the mediator to connect the web application to IoT devices, so create the IBM Watson IoT platform. | IBM Watson IoT Platform Login ID & Password | 1.Login to IBM Cloud 2.Click Catalog 3.Search IoT and click create 4.Go to resource list and search Internet of Things platform 5.Press Launch and click Sign in IBM Watson Platform | https://eynrcc.internetofthings.ibmcloud.com/dashboard/devices/browse/add | User should be navigated to IBM IoT Watson Platform | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_OO4 | Functional | IBM Watson | In order to connect the IoT device to the IBM cloud, create a device in the IBM Watson IoT platform and get the device credentials. | IBM Watson IoT Platform Login ID & Password | 1.Login to IBM Watson Platform 2. Click Add Device 3.Enter the details and click Finish. Create Device ID & Device type 4.Turn on Device Simulator and click simulation running. Enter the values of temperature, Humidity , Soil moisture 5.Click Send & Save. Verify the displayed result of the levels | Temperature, Humidity , sensor values are generated randomly in simulation | Temperature, Humidity , sensor values should be randomly generated | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_OO5 | Functional | IBM Cloud(Node Red) | Configure the connection security and create API keys that are used in the Node-RED service for accessing the IBM IoT Platform. | Node Red Installation | 1.Install node red and open node red in command prompt 2.Select IBM input in IoT | https://cloud.ibm.com/developer/appservice/create-app?starterKit=59c9d5bd-4d31-3611-897a-f94eea80dc9f&defaultLanguage=undefined | User should be able to see the Node Red page | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_OO6 | Functional | Node Red | Create a Node-RED service. | Node Red Installation | 1.Select IBM IoT input in Node. In IBM IoT Watson Platform, go to apps and click on generate API keys. 2.Copy & paste generated API key and token in the IBM IoT input. After entering all details, click the done button. 3.Add debug to the IBM IoT and rename as Msg.payload and click on done. Click gauge from the dashboard and fill the details & add functions to the gauge. Check the generated values from the debug message. 4.Edit function node, connect them, add another gauge and functions, name them as "Temperature", "Soil moisture" &"Humidity" 5.Finally add light ON/OFF buttons to the IBM IoT and debug. Verify the output from NODE RED using Local host link | Values of sensors and button for light ON/OFF is displayed | Values of sensors and button for light ON/OFF should be displayed | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_OO7 | Functional | Python 3.7.0 | Develop a python script to publish random sensor data such as temperature, humidity level, soil moisture to the IBM IoT platform | Python 3.7.0(64 bit) installation | 1.Download and install Python 3.7.0 2.Develop python code | https://www.python.org/downloads/release/python-370/ | User should be able to develop a python code | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_OO8 | Functional | Python 3.7.0 | After developing python code, commands are received just print the statements which represent the control of the devices. | Python 3.7.0(64 bit) installation | 1.Downlinstall Python 3.7.0 2.After python code | Get the output from the code | User should be able to get the results from the developed code | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_OO9 | Functional | IBM Cloudant DB | Publish Data to The IBM Cloud | IBM Cloud Login ID & Password | 1.Run the python code 2.Verify the displayed output | Publishment of python code | User should be able to publish the code | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_O10 | Web UI | Node Red & MIT Inventor | Create Web UI in Node- Red | MIT Inventor Login ID & password | 1.Go to Node Red. Select http in & http response. Add functions and select another http in and http response. Connect them to IBM IoT output and function.Print the command statements such as light ON/OFF and sensor 2.Go to MIT app inventor and create frontend using buttons,horizontal arrangement, text bar, etc. Add blocks and so on to create back end. Verify the output | Sensors values and command values can be seen in the mobile application | Sensors values and command values should be seen in the mobile application | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M
TC_O11 | Functional | IBM Cloudant DB | Configure the Node-RED flow to receive data from the IBM IoT platform and also use Cloudant DB nodes to store the received sensor data in the cloudant DB | IBM Cloud Login ID & Password | 1.Go to IBM cloud, search Cloudant in Catalog, Add new dashboard, go to Node Red 2.Connect to cloudant and verify the results | Cloudant is connected by NODE RED | User should be able to connect the Cloudant and Node Red | Working as expected | Pass | Results verified | No |  | Leelavathy.A, Kaviyasri.G, Lawanya.C, Ilakiyaselvi.M

## Testscearnios
Test Scenarios
1 | Verify user is able to see login page
2 | Verify user is able to loginto application or not?
3 | Verify user is able to navigate to create your account page?
4 | Verify user is able to recovery password
5 | Veriify login page elements
Search
1 | Verify user is able to search by entering keywords in search box
2 | Verify user is able to see suggestions based on keyword entered in search box
3 | Verify user is able to see related auto suggestions displaying based on keyword entered in search box
4 | Verify user is able to see no matches found message when no results are matching with entered keyword
5 | Verify user is able to see seach detailed page when nothing entered in textbox